## FMEA Instructions
A typical FMEA consists of the following steps:
1. Identify the process to be analyzed. Typically, this is a main process for the organization.
2. Assemble and train the team. Processes usually cross functional boundaries and, therefore, the analysis should be performed by a team of relevant personnel. No one person or persons from a single functional area will have the knowledge needed to perform the analysis.
3. Develop a detailed process flowchart, including all steps in the process.
4. Identify each step (or function) in the process.
5. Identify potential failures (or failure modes) at each step in the process. Note that there may be more than one potential failure at each step.
6. Determine the worst potential consequence (or effect) of each possible failure.
7. Identify the cause(s) (contributory factors) of each potential failure. A root-cause analysis can be helpful in this step. Note that there may be more than one cause for each potential failure.
8. Identify any failure “controls” currently present. A control reduces the likelihood of causes or failure occurring, reduces the severity of an effect, or enables the detection of the occurrence of a cause or failure before it leads to the adverse effect.
9. Rate the severity of each effect (on a scale of 1–10, with 10 being the most severe). This rating should reflect the impact of any controls that reduce the severity of the effect.
10. Rate the likelihood (occurrence score) of each cause occurring (on a scale of 1-10, with 10 being certain to occur). This rating should reflect the impact of any controls that reduce the likelihood of occurrence.
11. Rate the effectiveness of each control (on a scale of 1–10, with 1 being an error-free detection system).
12. Multiply the three ratings by one another to obtain the risk priority number (RPN) for each cause or contributory factor.
13. Use the RPNs to prioritize problems for corrective action. All causes resulting in an effect with a severity of 10 should be high on the priority list, regardless of RPN.
14. Develop an improvement plan to address the targeted causes (who, when, how assessed, etc.).

## FEMA Worksheet
FMEA PROJECT
FMEA goal
Project leader
Team members
Date prepared
Results
Step(s) in the Process | Potential Failure Mode | Failure Cause(s) | Failure Effect(s) | Severity (1–10) | Probability of Occurrence (1–10) | Existing Control(s) | Probability of Detection (1–10) | Risk Priority Number (RPN) | Recommended Actions | Responsibility | Target Date | Outcome Measure | Action Complete | New Severity | New Occurrence | New Detection | New RPN
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0

## FEMA Example
FMEA PROJECT: Patient Fall Reduction
FMEA goal |  | 50% reduction of preventable patient falls in 2008
Project leader |  | Abby Lin
Team members |  | Kevin Smith, Jessie Jones, Brit Johnson
Date prepared |  | 2007-10-13
Results
Step(s) in the Process | Potential Failure Mode | Failure Cause(s) | Failure Effect(s) | Severity (1–10) | Probability of Occurrence (1–10) | Existing Control(s) | Probability of Detection (1–10) | Risk Priority Number (RPN) | Recommended Actions | Responsibility | Target Date | Outcome Measure | Action Complete | New Severity | New Occurrence | New Detection | New RPN
Fall assessment upon admission | Fall | Anethesia | Potential injury | 10 | 1 |  | 1 | 10 | Amublation assistance for the first 24 hours after admission | [7 empty] | 0
| No asssesment | Lack of complete patient history information | Inaccurate fall risk assigned to patient | 8 | 2 |  | 2 | 32 | Chart audits to assure admission evalution | [7 empty] | 0
Incorrect fall assessment | Fall | Slip or trip due to wet floor, trip hazards, patient urgency | Potential injury | 8 | 1 | Patients assigned fall risk category | 1 | 8 | [8 empty] | 0
| Patient not identified as having a high fall risk | Incorrect use of assessment | Lack of fall interventions | 7 | 2 |  | 2 | 28 | Training on fall assessment and prevention. Monitor falls to insure that risks and preventions are identified | [7 empty] | 0
Medication issues | Over-medication | Patients are admitted in an agitated state requiring stronger medication | Drowsiness leading to a fall | 8 | 3 |  | 2 | 48 | Medication training to make clinicians aware of sedative potential of medications. Post alerts on patients with high medication. Include fall risk in shift assessment | [7 empty] | 0
| Medications increase ataxia and/or drowsiness | Medications have sedating and ataxic effects. | Potential injury | 9 | 8 |  | 2 | 144 | Staff training on medication effects.Include fall risk in shift assessment | [7 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0
[8 empty] | 0 | [8 empty] | 0